## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Environment Set Up | 5 days | 02 December 2020 08:00 | 08 December 2020 17:00 |  | 1
2 | Yes | Auto Scheduled | Device Set Up | 2 days | 02 December 2020 08:00 | 03 December 2020 17:00 |  | 2
3 | Yes | Auto Scheduled | Network Configuration | 2 days | 04 December 2020 08:00 | 07 December 2020 17:00 | 2 | 2
4 | Yes | Auto Scheduled | Device Testing On Ursalink | 1 day | 08 December 2020 08:00 | 08 December 2020 17:00 | 3 | 2
5 | Yes | Manually Scheduled | Connecting Sensors To Gateway | 3 days | 03 December 2020 09:00 | 08 December 2020 09:00 |  | 2
6 | Yes | Manually Scheduled | Table Design | 1 day | 04 December 2020 09:00 | 07 December 2020 09:00 |  | 1
7 | Yes | Auto Scheduled | Project Set Up | 1.5 days | 07 December 2020 09:00 | 08 December 2020 14:00 | 6 | 1
8 | Yes | Auto Scheduled | Development & Implementation | 8 days | 08 December 2020 14:00 | 18 December 2020 14:00 |  | 1
9 | Yes | Auto Scheduled | Administration | 8 days | 08 December 2020 14:00 | 18 December 2020 14:00 |  | 2
10 | Yes | Auto Scheduled | Login | 3 days | 08 December 2020 14:00 | 11 December 2020 14:00 | 7 | 3
11 | Yes | Auto Scheduled | Manage Users & Access | 2 days | 08 December 2020 14:00 | 10 December 2020 14:00 | 7 | 3
12 | Yes | Auto Scheduled | Manage Devices | 3 days | 08 December 2020 14:00 | 11 December 2020 14:00 | 7 | 3
13 | Yes | Auto Scheduled | Manage References | 1 day | 08 December 2020 14:00 | 09 December 2020 14:00 | 7 | 3
14 | Yes | Auto Scheduled | Manage Plantations/Fields | 1 day | 09 December 2020 14:00 | 10 December 2020 14:00 | 13 | 3
15 | Yes | Auto Scheduled | Manage Crops And Element Values | 1 day | 11 December 2020 14:00 | 14 December 2020 14:00 | 12 | 3
16 | Yes | Auto Scheduled | Manage Alerts & Notifications | 1 day | 10 December 2020 14:00 | 11 December 2020 14:00 | 14 | 3
17 | Yes | Auto Scheduled | Audit Trail | 3 days | 10 December 2020 14:00 | 15 December 2020 14:00 | 11 | 3
18 | Yes | Auto Scheduled | Admin Reports | 3 days | 15 December 2020 14:00 | 18 December 2020 14:00 | 17 | 3
19 | Yes | Auto Scheduled | Integration of Device with Web App | 11.5 days | 07 December 2020 09:00 | 22 December 2020 14:00 |  | 1
20 | Yes | Auto Scheduled | Integration with Endpoints | 9 days | 07 December 2020 09:00 | 18 December 2020 09:00 |  | 2
21 | Yes | Auto Scheduled | Gateway | 2 days | 07 December 2020 09:00 | 09 December 2020 09:00 | 6 | 3
22 | Yes | Auto Scheduled | Sensor node | 2 days | 09 December 2020 09:00 | 11 December 2020 09:00 | 21 | 3
23 | Yes | Auto Scheduled | PH | 1 day | 11 December 2020 09:00 | 14 December 2020 09:00 | 22 | 3
24 | Yes | Auto Scheduled | Light | 1 day | 14 December 2020 09:00 | 15 December 2020 09:00 | 23 | 3
25 | Yes | Auto Scheduled | NPK | 1 day | 15 December 2020 09:00 | 16 December 2020 09:00 | 24 | 3
26 | Yes | Auto Scheduled | Humidity | 1 day | 16 December 2020 09:00 | 17 December 2020 09:00 | 25 | 3
27 | Yes | Auto Scheduled | Temp And Humidity | 1 day | 17 December 2020 09:00 | 18 December 2020 09:00 | 26 | 3
28 | Yes | Auto Scheduled | NPK | 6 days | 14 December 2020 14:00 | 22 December 2020 14:00 |  | 2
29 | Yes | Auto Scheduled | Manage NPK Values + Keep Historic | 4 days | 14 December 2020 14:00 | 18 December 2020 14:00 | 5,6,7,12,14,15 | 3
30 | Yes | Auto Scheduled | Trigger Action for NPK (keep history when action made) | 2 days | 18 December 2020 14:00 | 22 December 2020 14:00 | 29 | 3
31 | Yes | Auto Scheduled | Humidity | 2 days | 14 December 2020 14:00 | 16 December 2020 14:00 |  | 2
32 | Yes | Auto Scheduled | Manage Humidity + Keep Data of Findings | 1 day | 14 December 2020 14:00 | 15 December 2020 14:00 | 5,6,7,12,14,15 | 3
33 | Yes | Auto Scheduled | Trigger Pump/ Automate / Manual / Alert / Screen Details / Audit | 1 day | 15 December 2020 14:00 | 16 December 2020 14:00 | 32 | 3
34 | Yes | Auto Scheduled | Integration with AccuWeather | 1.5 days | 14 December 2020 14:00 | 16 December 2020 09:00 |  | 3
35 | Yes | Auto Scheduled | Check Weather to Trigger Water Pump + Sunlight? + Audit | 1.5 days | 14 December 2020 14:00 | 16 December 2020 09:00 | 15 | 4
36 | Yes | Auto Scheduled | Temperature | 1 day | 14 December 2020 14:00 | 15 December 2020 14:00 |  | 2
37 | Yes | Auto Scheduled | Manage Temp | 1 day | 14 December 2020 14:00 | 15 December 2020 14:00 | 5,6,7,12,14,15 | 3
38 | Yes | Auto Scheduled | EC | 4 days | 14 December 2020 14:00 | 18 December 2020 14:00 |  | 2
39 | Yes | Auto Scheduled | Manage EC | 3 days | 14 December 2020 14:00 | 17 December 2020 14:00 | 5,6,7,12,14,15 | 3
40 | Yes | Auto Scheduled | Automation / Warning | 1 day | 17 December 2020 14:00 | 18 December 2020 14:00 | 39 | 3
41 | Yes | Auto Scheduled | PH | 3 days | 14 December 2020 14:00 | 17 December 2020 14:00 |  | 2
42 | Yes | Auto Scheduled | Manage PH | 1 day | 14 December 2020 14:00 | 15 December 2020 14:00 | 5,6,7,12,14,15 | 3
43 | Yes | Auto Scheduled | Automate / Manual | 1 day | 15 December 2020 14:00 | 16 December 2020 14:00 | 42 | 3
44 | Yes | Auto Scheduled | History | 1 day | 16 December 2020 14:00 | 17 December 2020 14:00 | 43 | 3
45 | Yes | Auto Scheduled | Integration of All Elements on the Web App | 4 days | 17 December 2020 14:00 | 23 December 2020 14:00 |  | 1
46 | Yes | Auto Scheduled | Integration | 1 day | 17 December 2020 14:00 | 18 December 2020 14:00 | 44 | 2
47 | Yes | Auto Scheduled | Testing | 3 days | 18 December 2020 14:00 | 23 December 2020 14:00 | 46 | 2
48 | Yes | Auto Scheduled | Reporting | 5 days | 17 December 2020 14:00 | 24 December 2020 14:00 | 44 | 1
49 | Yes | Auto Scheduled | AI | 10 days | 16 December 2020 09:00 | 11 January 2021 09:00 |  | 1
50 | Yes | Auto Scheduled | Modelling | 10 days | 16 December 2020 09:00 | 11 January 2021 09:00 | 35 | 2
51 | Yes | Auto Scheduled | OTHER (Not yet Planned) | 20 days | 11 January 2021 09:00 | 08 February 2021 09:00 | 50 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | <New Resource> | < | Work |  |  |  |  | 100% | Rs0.00/h | 0
2 | Andy Anna | AA | Work |  |  |  |  | 100% | Rs0.00/h | 0
3 | Varun Puttur | VP | Work |  |  |  |  | 100% | Rs0.00/h | 0
4 | Alexandre Bonne | A | Work |  |  |  |  | 100% | Rs0.00/h | 0
5 | Jeeresh Luchmun | JL | Work |  |  |  |  | 100% | Rs0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units | Actual date start | Acutal date finish | Days of work | hours
Device Set Up | Andy Anna | 0 | 16h | 100%
Device Set Up | Alexandre Bonne | 0 | 16h | 100% | 2020-12-02 |  | 1
Device Set Up | Jeeresh Luchmun | 0 | 16h | 100%
Network Configuration | Alexandre Bonne | 0 | 8h | 100%
Network Configuration | Andy Anna | 0 | 8h | 100%
Network Configuration | Jeeresh Luchmun | 0 | 16h | 100%
Device Testing On Ursalink | Alexandre Bonne | 0 | 8h | 100%
Device Testing On Ursalink | Andy Anna | 0 | 8h | 100%
Device Testing On Ursalink | Jeeresh Luchmun | 0 | 8h | 100%
Device Testing On Ursalink | Varun Puttur | 0 | 8h | 100%
Connecting Sensors To Gateway | Andy Anna | 0 | 16h | 100%
Table Design | Alexandre Bonne | 0 | 8h | 100% | 2020-12-04 | 2020-12-04 | 0.5 | 4h
Table Design | Varun Puttur | 0 | 8h | 100%
Project Set Up | Alexandre Bonne | 0 | 4h | 100% | 2020-12-08 | 2020-12-08
Project Set Up | Varun Puttur | 0 | 4h | 100%
Login | Varun Puttur | 0 | 8h | 100%
Login | Jeeresh Luchmun | 0 | 24h | 100%
Manage Users & Access | Varun Puttur | 0 | 3h | 100%
Manage Users & Access | Jeeresh Luchmun | 0 | 16h | 100%
Manage Devices | Alexandre Bonne | 0 | 24h | 100%
Manage Devices | Varun Puttur | 0 | 8h | 100%
Manage References | Jeeresh Luchmun | 0 | 8h | 100%
Manage References | Varun Puttur | 0 | 3h | 100%
Manage Plantations/Fields | Jeeresh Luchmun | 0 | 8h | 100%
Manage Plantations/Fields | Alexandre Bonne | 0 | 8h | 100%
Manage Crops And Element Values | Alexandre Bonne | 0 | 0h | 100%
Manage Crops And Element Values | Varun Puttur | 0 | 3h | 100%
Manage Alerts & Notifications | Jeeresh Luchmun | 0 | 8h | 100%
Manage Alerts & Notifications | Alexandre Bonne | 0 | 8h | 100%
Audit Trail | Varun Puttur | 0 | 0h | 100%
Audit Trail | Jeeresh Luchmun | 0 | 19h | 100%
Admin Reports | Varun Puttur | 0 | 16h | 100%
Admin Reports | Alexandre Bonne | 0 | 21h | 100%
Integration with Endpoints | Andy Anna | 0 | 72h | 100%
Gateway | Andy Anna | 0 | 16h | 100%
Sensor node | Andy Anna | 0 | 16h | 100%
PH | Andy Anna | 0 | 8h | 100%
Light | Andy Anna | 0 | 8h | 100%
NPK | Andy Anna | 0 | 8h | 100%
Humidity | Andy Anna | 0 | 8h | 100%
Temp And Humidity | Andy Anna | 0 | 8h | 100%
Manage NPK Values + Keep Historic | Varun Puttur | 0 | 16h | 100%
Trigger Action for NPK (keep history when action made) | Varun Puttur | 0 | 8h | 100%
Manage Humidity + Keep Data of Findings | Andy Anna | 0 | 8h | 100%
Trigger Pump/ Automate / Manual / Alert / Screen Details / Audit | Andy Anna | 0 | 8h | 100%
Check Weather to Trigger Water Pump + Sunlight? + Audit | Alexandre Bonne | 0 | 12h | 100% | 2020-12-15 |  | 0.6
Manage Temp | Jeeresh Luchmun | 0 | 0h | 100%
Manage EC | Varun Puttur | 0 | 8h | 100%
Manage PH | Andy Anna | 0 | 8h | 100%
Automate / Manual | Andy Anna | 0 | 8h | 100%
History | Andy Anna | 0 | 8h | 100%
Modelling | Alexandre Bonne | 0 | 80h | 100%
OTHER (Not yet Planned) | Alexandre Bonne | 0 | 160h | 100%
OTHER (Not yet Planned) | Andy Anna | 0 | 160h | 100%
OTHER (Not yet Planned) | Jeeresh Luchmun | 0 | 157h | 100%
OTHER (Not yet Planned) | Varun Puttur | 0 | 149h | 100%
Formulas:
Actual date start = [1]Sheet1!$H7