## Sheet1
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Actual date start | Acutal date finish | Days of work | hours
Auto Scheduled | Environment Set Up | 5 days | Wed 02/12/20 | Tue 08/12/20
Auto Scheduled | Device Set Up | 2 days | Wed 02/12/20 | Thu 03/12/20 |  | Andy Anna,Alexandre Bonne,Jeeresh Luchmun | 2020-12-02 |  | 1
Auto Scheduled | Network Configuration | 2 days | Fri 04/12/20 | Mon 07/12/20 | 2 | Alexandre Bonne,Andy Anna,Jeeresh Luchmun
Auto Scheduled | Device Testing On Ursalink | 1 day | Tue 08/12/20 | Tue 08/12/20 | 3 | Alexandre Bonne,Andy Anna,Jeeresh Luchmun,Varun Puttur
Manually Scheduled | Connecting Sensors To Gateway | 3 days | Thu 03/12/20 | Tue 08/12/20 |  | Andy Anna
Manually Scheduled | Table Design | 0.5 days | Fri 04/12/20 | Fri 04/12/20 |  | Alexandre Bonne,Varun Puttur | 2020-12-04 | 2020-12-04 | 0.5 | 2 hours
Auto Scheduled | Project Set Up | 1.5 days | Fri 04/12/20 | Tue 08/12/20 | 6 | Alexandre Bonne,Varun Puttur
Auto Scheduled | Development & Implementation | 7 days | Tue 08/12/20 | Thu 17/12/20
Auto Scheduled | Administration | 7 days | Tue 08/12/20 | Thu 17/12/20
Auto Scheduled | Login | 2 days | Tue 08/12/20 | Thu 10/12/20 | 7 | Varun Puttur
Auto Scheduled | Manage Users & Access | 2 days | Tue 08/12/20 | Thu 10/12/20 | 7 | Varun Puttur
Auto Scheduled | Manage Devices | 2 days | Tue 08/12/20 | Thu 10/12/20 | 7 | Alexandre Bonne
Auto Scheduled | Manage References | 1 day | Tue 08/12/20 | Wed 09/12/20 | 7 | Jeeresh Luchmun
Auto Scheduled | Manage Plantations/Fields | 1 day | Wed 09/12/20 | Thu 10/12/20 | 13 | Jeeresh Luchmun
Auto Scheduled | Manage Crops And Element Values | 1 day | Thu 10/12/20 | Fri 11/12/20 | 12 | Alexandre Bonne
Auto Scheduled | Manage Alerts & Notifications | 1 day | Thu 10/12/20 | Fri 11/12/20 | 14 | Jeeresh Luchmun
Auto Scheduled | Audit Trail | 3 days | Thu 10/12/20 | Tue 15/12/20 | 11 | Varun Puttur
Auto Scheduled | Admin Reports | 2 days | Tue 15/12/20 | Thu 17/12/20 | 17 | Varun Puttur
Auto Scheduled | Integration of Device with Web App | 3 days | Fri 11/12/20 | Wed 16/12/20
Auto Scheduled | NPK | 3 days | Fri 11/12/20 | Wed 16/12/20
Auto Scheduled | Manage NPK Values + Keep Historic | 2 days | Fri 11/12/20 | Tue 15/12/20 | 5,6,7,12,14,15 | Varun Puttur
Auto Scheduled | Trigger Action for NPK (keep history when action made) | 1 day | Tue 15/12/20 | Wed 16/12/20 | 21 | Varun Puttur
Auto Scheduled | Humidity | 2 days | Fri 11/12/20 | Tue 15/12/20
Auto Scheduled | Manage Humidity + Keep Data of Findings | 1 day | Fri 11/12/20 | Mon 14/12/20 | 5,6,7,12,14,15 | Andy Anna
Auto Scheduled | Trigger Pump/ Automate / Manual / Alert / Screen Details / Audit | 1 day | Mon 14/12/20 | Tue 15/12/20 | 24 | Andy Anna
Auto Scheduled | Integration with AccuWeather | 1.5 days | Fri 11/12/20 | Mon 14/12/20
Auto Scheduled | Check Weather to Trigger Water Pump + Sunlight? + Audit | 1.5 days | Fri 11/12/20 | Mon 14/12/20 | 15 | Alexandre Bonne
Auto Scheduled | Temperature | 1 day | Fri 11/12/20 | Mon 14/12/20
Auto Scheduled | Manage Temp | 1 day | Fri 11/12/20 | Mon 14/12/20 | 5,6,7,12,14,15 | Jeeresh Luchmun
Auto Scheduled | EC | 2 days | Fri 11/12/20 | Tue 15/12/20
Auto Scheduled | Manage EC | 1 day | Fri 11/12/20 | Mon 14/12/20 | 5,6,7,12,14,15 | Varun Puttur
Auto Scheduled | Automation / Warning | 1 day | Mon 14/12/20 | Tue 15/12/20 | 31
Auto Scheduled | PH | 3 days | Fri 11/12/20 | Wed 16/12/20
Auto Scheduled | Manage PH | 1 day | Fri 11/12/20 | Mon 14/12/20 | 5,6,7,12,14,15 | Andy Anna
Auto Scheduled | Automate / Manual | 1 day | Mon 14/12/20 | Tue 15/12/20 | 34 | Andy Anna
Auto Scheduled | History | 1 day | Tue 15/12/20 | Wed 16/12/20 | 35 | Andy Anna
Auto Scheduled | Integration of All Elements on the Web App | 4 days | Wed 16/12/20 | Tue 22/12/20
Auto Scheduled | Integration | 1 day | Wed 16/12/20 | Thu 17/12/20 | 36
Auto Scheduled | Testing | 3 days | Thu 17/12/20 | Tue 22/12/20 | 38
Auto Scheduled | Reporting | 5 days | Wed 16/12/20 | Wed 23/12/20 | 36
Auto Scheduled | AI | 10 days | Mon 14/12/20 | Wed 30/12/20
Auto Scheduled | Modelling | 10 days | Mon 14/12/20 | Wed 30/12/20 | 27 | Alexandre Bonne
Auto Scheduled | OTHER (Not yet Planned) | 20 days | Wed 30/12/20 | Thu 04/02/21 | 42 | Alexandre Bonne,Andy Anna,Jeeresh Luchmun,Varun Puttur